## Gantt Chart
GANTT CHART (The Impact of Weak Authentication on IoT Devices Security)
PROJECT TITLE |  | The Impact of Weak Authentication on IoT Device Security |  |  |  |  | COMPANY NAME | [6 empty] | University’s Data Science Department
PROJECT MANAGER |  | Mrs.Thiri Win |  |  |  |  | DATE | [6 empty] | 2026-05-15
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | PREPARATION
1.1 | Identify Research Topic | Project Manager | 2026-05-08 | 2026-06-23 | 45 | 100%
1.2 | Define Research Objectives | Project Assistant | 2026-05-08 | 2026-06-23 | 45 | 100%
1.3 | Project Scope Definition | Project Assistant | 2026-05-08 | 2026-06-23 | 45 | 100%
1.4 | Research Data | Project Assistant | 2026-05-08 | 2026-06-23 | 45 | 100%
1.5 | Identify Research Questions | Project Manager | 2026-05-08 | 2026-06-23 | 45 | 100%
2 | PLANNING
2.1 | Research Proposal | Project Assistant | 2026-05-08 | 2026-06-23 | 45 | 100%
2.1.1 | Research For Primary Report | Project Assistant | 2026-05-08 | 2026-06-23 | 45 | 100%
2.1.2 | Research For Secondary Report | Project Assistant | 2026-05-08 | 2026-06-10 | 32 | 100%
2.2 | Research Methodology Selection | Project Assistant | 2026-05-08 | 2026-06-23 | 45 | 100%
2.3 | Create Survey Questions | Project Assistant | 2026-05-22 | 2026-06-23 | 31 | 100%
2.3.1 | Gather Survey Response | Project Assistant | 2026-05-27 | 2026-06-23 | 26 | 100%
2.4 | Work Breakdown Structure | Project Assistant | 2026-06-11 | 2026-06-23 | 12 | 100%
2.5 | Timeline & Milestones | Project Assistant | 2026-06-12 | 2026-06-23 | 11 | 100%
2.5.1 | Gantt Chart | Project Assistant | 2026-06-12 | 2026-06-23 | 11 | 100%
2.5.2 | Project Charter | Project Assistant | 2026-06-12 | 2026-06-23 | 11 | 100%
2.6 | Identify Benefits | Project Assistant | 2026-06-13 | 2026-06-23 | 10 | 100%
2.7 | Identify Risks | Project Assistant | 2026-06-13 | 2026-06-23 | 10 | 100%
2.8 | Mitigation Plan | Project Assistant | 2026-06-13 | 2026-06-23 | 10 | 100%
3 | DEVELOPMENT
3.1 | In Depth Literature Analysis | Project Assistant |  |  | 0 | 0%
3.2 | Threat Modeling | Cybersecurity/IoT Faculty Advisor |  |  | 0 | 0%
3.3 | Vulnerability Assessment | IoT Security Specialist |  |  | 0 | 0%
3.4 | Case Study Analysis | Data Analyst |  |  | 0 | 0%
3.5 | Security Solutions Design | Project Manager |  |  | 0 | 0%
3.6 | Proof of Concept | IoT Security Specialist |  |  | 0 | 0%
4 | TESTING
4.1 | Data Analysis and Synthesis | Data Analyst |  |  | 0 | 0%
4.2 | Finding Validation | Project Manager |  |  | 0 | 0%
4.3 | Expert Review | Cybersecurity Consultant |  |  | 0 | 0%
4.4 | Peer Review Process | Academic Peer Reviewers |  |  | 0 | 0%
4.5 | Results Verification | Cybersecurity/IoT Faculty Advisor |  |  | 0 | 0%
4.6 | Recommendation Refinement | Project Manager |  |  | 0 | 0%
5 | RELEASE
5.1 | Research Paper Writing | Project Manager |  |  | 0 | 0%
5.2 | Presentation Creation | Project Assistant |  |  | 0 | 0%
5.3 | Publication Planning | Project Manager |  |  | 0 | 0%
5.4 | Dissemination Strategy | Department Coordina |  |  | 0 | 0%
5.5 | Final Documentation | Project Assistant |  |  | 0 | 0%
5.6 | Project Closure | Project Manager |  |  | 0 | 0%